## Project_Plan
|  | Y24-PI1 | Y24-PI1 | Y24-PI1 | Y24-PI1 | Y24-PI1 | Y24-PI1 | Y24-PI1 | Y24-PI1 | Y24-PI1 | Y24-PI1 IP Sprint | Y24-PI1 IP Sprint | Y24-PI2 | Y24-PI2 | Y24-PI2 | Y24-PI2 | Y24-PI2 | Y24-PI2 | Y24-PI2 | Y24-PI2 | Y24-PI2 | Y24-PI2 | Y24-PI2 | Y24-PI2 | Y24-PI2 IP Sprint | Y24-PI2 IP Sprint | Y24-PI3 | Y24-PI3 | Y24-PI3 | Y24-PI3 | Y24-PI3 | Y24-PI3 | Y24-PI3 | Y24-PI3 | Y24-PI3 | Y24-PI3 | Y24-PI3 | Y24-PI3 | Y24-PI3 IP Sprint | Y24-PI3 IP Sprint | Y24-PI4 | Y24-PI4 | Y24-PI4 | Y24-PI4 | Y24-PI4 | Y24-PI4 | Y24-PI4 | Y24-PI4 | Y24-PI4 IP Sprint | Y24-PI4 IP Sprint | Y25-PI1 | Y25-PI1 | Y25-PI1 | Y25-PI1 | Y25-PI1 | Y25-PI1 | Y25-PI1 | Y25-PI1 | Y25-PI1 | Y25-PI1 | Y25-PI1 | Y25-PI1 | Y25-PI1 IP Sprint | Y25-PI1 IP Sprint | Y25-PI2 | Y25-PI2 | Y25-PI2 | Y25-PI2 | Y25-PI2 | Y25-PI2 | Y25-PI2 | Y25-PI2 | Y25-PI2 | Y25-PI2 | Y25-PI2 | Y25-PI2 | Y25-PI2 IP Sprint | Y25-PI2 IP Sprint | Y25-PI3 | Y25-PI3 | Y25-PI3 | Y25-PI3 | Y25-PI3 | Y25-PI3 | Y25-PI3 | Y25-PI3 | Y25-PI3 | Y25-PI3 | Y25-PI3 | Y25-PI3 | Y25-PI3 IP Sprint | Y25-PI3 IP Sprint | Y25-PI4 | Y25-PI4 | Y25-PI4 | Y25-PI4 | Y25-PI4 | Y25-PI4 | Y25-PI4 | Y25-PI4 | Y25-PI4 IP Sprint | Y25-PI4 IP Sprint | Y26-PI1 | Y26-PI1 | Y26-PI1 | Y26-PI1 | Y26-PI1 | Y26-PI1 | Y26-PI1 | Y26-PI1 | Y26-PI1 | Y26-PI1 | Y26-PI1 | Y26-PI1 | Y26-PI1 IP Sprint | Y26-PI1 IP Sprint | Y26-PI2 | Y26-PI2 | Y26-PI2 | Y26-PI2 | Y26-PI2 | Y26-PI2 | Y26-PI2 | Y26-PI2 | Y26-PI2 | Y26-PI2 | Y26-PI2 | Y26-PI2 | Y26-PI2 IP Sprint | Y26-PI2 IP Sprint | Y26-PI3 | Y26-PI3 | Y26-PI3 | Y26-PI3 | Y26-PI3 | Y26-PI3 | Y26-PI3 | Y26-PI3 | Y26-PI3 | Y26-PI3 | Y26-PI3 | Y26-PI3 | Y26-PI3 IP Sprint | Y26-PI3 IP Sprint | Y26-PI4 | Y26-PI4 | Y26-PI4 | Y26-PI4 | Y26-PI4 | Y26-PI4 | Y26-PI4 | Y26-PI4 | Y26-PI4 IP Sprint | Y26-PI4 IP Sprint
[12 empty] | PI Planning | [13 empty] | PI Planning | [13 empty] | PI Planning | [9 empty] | PI Planning | [13 empty] | PI Planning | [13 empty] | PI Planning | [13 empty] | PI Planning | [9 empty] | PI Planning | [13 empty] | PI Planning | [13 empty] | PI Planning | [13 empty] | PI Planning | [9 empty] | PI Planning
|  | S2 | S3 | S3 | S4 | S4 | S5 | S5 | S6 | S6 | IP | IP | S1 | S1 | S2 | S2 | S3 | S3 | S4 | S4 | S5 | S5 | S6 | S6 | IP | IP | S1 | S1 | S2 | S2 | S3 | S3 | S4 | S4 | S5 | S5 | S6 | S6 | IP | IP | S1 | S1 | S2 | S2 | S3 | S3 | S4 | S4 | IP | IP | S1 | S1 | S2 | S2 | S3 | S3 | S4 | S4 | S5 | S5 | S6 | S6 | IP | IP | S1 | S1 | S2 | S2 | S3 | S3 | S4 | S4 | S5 | S5 | S6 | S6 | IP | IP | S1 | S1 | S2 | S2 | S3 | S3 | S4 | S4 | S5 | S5 | S6 | S6 | IP | IP | S1 | S1 | S2 | S2 | S3 | S3 | S4 | S4 | IP | IP | S1 | S1 | S2 | S2 | S3 | S3 | S4 | S4 | S5 | S5 | S6 | S6 | IP | IP | S1 | S1 | S2 | S2 | S3 | S3 | S4 | S4 | S5 | S5 | S6 | S6 | IP | IP | S1 | S1 | S2 | S2 | S3 | S3 | S4 | S4 | S5 | S5 | S6 | S6 | IP | IP | S1 | S1 | S2 | S2 | S3 | S3 | S4 | S4 | IP | IP
|  | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December
Team | 2024 | CW01 | CW02 | CW03 | CW04 | CW05 | CW06 | CW07 | CW08 | CW09 | CW10 | CW11 | CW12 | CW13 | CW14 | CW15 | CW16 | CW17 | CW18 | CW19 | CW20 | CW21 | CW22 | CW23 | CW24 | CW25 | CW26 | CW27 | CW28 | CW29 | CW30 | CW31 | CW32 | CW33 | CW34 | CW35 | CW36 | CW37 | CW38 | CW39 | CW40 | CW41 | CW42 | CW43 | CW44 | CW45 | CW46 | CW47 | CW48 | CW49 | CW50 | CW51 | CW52 | CW01 | CW02 | CW03 | CW04 | CW05 | CW06 | CW07 | CW08 | CW09 | CW10 | CW11 | CW12 | CW13 | CW14 | CW15 | CW16 | CW17 | CW18 | CW19 | CW20 | CW21 | CW22 | CW23 | CW24 | CW25 | CW26 | CW27 | CW28 | CW29 | CW30 | CW31 | CW32 | CW33 | CW34 | CW35 | CW36 | CW37 | CW38 | CW39 | CW40 | CW41 | CW42 | CW43 | CW44 | CW45 | CW46 | CW47 | CW48 | CW49 | CW50 | CW51 | CW52 | CW01 | CW02 | CW03 | CW04 | CW05 | CW06 | CW07 | CW08 | CW09 | CW10 | CW11 | CW12 | CW13 | CW14 | CW15 | CW16 | CW17 | CW18 | CW19 | CW20 | CW21 | CW22 | CW23 | CW24 | CW25 | CW26 | CW27 | CW28 | CW29 | CW30 | CW31 | CW32 | CW33 | CW34 | CW35 | CW36 | CW37 | CW38 | CW39 | CW40 | CW41 | CW42 | CW43 | CW44 | CW45 | CW46 | CW47 | CW48 | CW49 | CW50 | CW51 | CW52 | CW53
Treville | Senthil | Product Owner (Port) | [24 empty] | Product Owner (Port) | [5 empty] | Vacation (Plan) |  |  | Product Owner (Port) |  |  | Y24-PI3 IP Sprint |  | Product Owner (Port) | [7 empty] | Y24-PI4 IP Sprint |  | Product Owner (Port) | Vacation (Plan) | [10 empty] | Y25-PI1 IP Sprint | [6 empty] | Vacation (Plan) | [6 empty] | Y25-PI2 IP Sprint | [7 empty] | Vacation (Plan) | [5 empty] | Y25-PI3 IP Sprint | [9 empty] | Y25-PI4 IP Sprint |  |  |  | Vacation (Plan) | [9 empty] | Y26-PI1 IP Sprint |  |  |  |  | Vacation (Plan) | [8 empty] | Y26-PI2 IP Sprint | [7 empty] | Vacation (Plan) | [5 empty] | Y26-PI3 IP Sprint | [9 empty] | Y26-PI4 IP Sprint |  |  |  | Vacation (Plan)
Treville | Sathya | AutoCore OS 6.1.X MV88Q515x RFM - EB Zoneo EBACQ-38978 |  |  | Scrum Master | [27 empty] | Vacation (Plan) | [5 empty] | Y24-PI3 IP Sprint | [9 empty] | Y24-PI4 IP Sprint |  |  | Vacation (Plan) | [10 empty] | Y25-PI1 IP Sprint | [6 empty] | Vacation (Plan) | [6 empty] | Y25-PI2 IP Sprint | [7 empty] | Vacation (Plan) | [5 empty] | Y25-PI3 IP Sprint | [9 empty] | Y25-PI4 IP Sprint |  |  |  | Vacation (Plan) | [9 empty] | Y26-PI1 IP Sprint |  |  |  |  | Vacation (Plan) | [8 empty] | Y26-PI2 IP Sprint | [7 empty] | Vacation (Plan) | [5 empty] | Y26-PI3 IP Sprint | [9 empty] | Y26-PI4 IP Sprint |  |  |  | Vacation (Plan)
Treville | Syam | ASCOS-9196 |  | AutoCore OS 6.1.X CORTEXM S32K35X DevDrop - WiTricity EBACQ-39027 EBACQ-39238 |  |  |  | AutoCore OS 6.1.X - SJA1110 - DD - EB PMG EBACQ-39536 EBACQ-39574 | [6 empty] | AutoCore OS 6.1.X - SJA1110 - RFM - EB PMG EBACQ-39536 EBACQ-39574 | [9 empty] | Y24-PI2 IP Sprint | [7 empty] | Vacation (Plan) | [5 empty] | Y24-PI3 IP Sprint | [9 empty] | Y24-PI4 IP Sprint |  |  | Vacation (Plan) | [10 empty] | Y25-PI1 IP Sprint | [6 empty] | Vacation (Plan) | [6 empty] | Y25-PI2 IP Sprint | [7 empty] | Vacation (Plan) | [5 empty] | Y25-PI3 IP Sprint | [9 empty] | Y25-PI4 IP Sprint |  |  |  | Vacation (Plan) | [9 empty] | Y26-PI1 IP Sprint |  |  |  |  | Vacation (Plan) | [8 empty] | Y26-PI2 IP Sprint | [7 empty] | Vacation (Plan) | [5 empty] | Y26-PI3 IP Sprint | [9 empty] | Y26-PI4 IP Sprint |  |  |  | Vacation (Plan)
Treville | Kavya | AutoCore OS 6.1 S32Z27XLLCE RFM - EB Zoneo EBACQ-37628 EBACQ-<TBD> ASCOS-8940 |  |  |  | AutoCore OS 6.1 RH850 RH850U2B8 DD - Innoviz EBACQ-39203 EBACQ-39240 | [6 empty] | AutoCore OS 6.1 RH850 RH850U2B8 RFM - Innoviz EBACQ-39203 EBACQ-39240 | [11 empty] | Y24-PI2 IP Sprint | [7 empty] | Vacation (Plan) | [5 empty] | Y24-PI3 IP Sprint | [9 empty] | Y24-PI4 IP Sprint |  |  | Vacation (Plan) | [10 empty] | Y25-PI1 IP Sprint | [6 empty] | Vacation (Plan) | [6 empty] | Y25-PI2 IP Sprint | [7 empty] | Vacation (Plan) | [5 empty] | Y25-PI3 IP Sprint | [9 empty] | Y25-PI4 IP Sprint |  |  |  | Vacation (Plan) | [9 empty] | Y26-PI1 IP Sprint |  |  |  |  | Vacation (Plan) | [8 empty] | Y26-PI2 IP Sprint | [7 empty] | Vacation (Plan) | [5 empty] | Y26-PI3 IP Sprint | [9 empty] | Y26-PI4 IP Sprint |  |  |  | Vacation (Plan)
Treville | Shiva | ASCOS-8524 | AutoCore OS 6.1.X CORTEXM S32K14X RFM TitanX EBACQ-37445 EBACQ-39044 |  |  |  |  | AutoCore OS 6.1.X S32K344 RFM - Internal PMG - EBACQ-39572 | [6 empty] | AutoCore OS 6.1.X S32NZ55-M7 DD - Internal PMG - EBACQ-37751 |  |  |  | AutoCore OS 6.1.X S32NZ55-M7 RFM - Internal PMG - EBACQ-37751 | [5 empty] | Y24-PI2 IP Sprint | [7 empty] | Vacation (Plan) | [5 empty] | Y24-PI3 IP Sprint | [9 empty] | Y24-PI4 IP Sprint |  |  | Vacation (Plan) | [10 empty] | Y25-PI1 IP Sprint | [6 empty] | Vacation (Plan) | [6 empty] | Y25-PI2 IP Sprint | [7 empty] | Vacation (Plan) | [5 empty] | Y25-PI3 IP Sprint | [9 empty] | Y25-PI4 IP Sprint |  |  |  | Vacation (Plan) | [9 empty] | Y26-PI1 IP Sprint |  |  |  |  | Vacation (Plan) | [8 empty] | Y26-PI2 IP Sprint | [7 empty] | Vacation (Plan) | [5 empty] | Y26-PI3 IP Sprint | [9 empty] | Y26-PI4 IP Sprint |  |  |  | Vacation (Plan)
Treville | Jeswin | AutoCore OS 6.1 CORTEXM S32NZ55M7 DD - EB PMG EBACQ-37751 EBACQ-37810 | AutoCore OS 6.1 MVQ6223 RFM - EB Zoneo EBACQ-37862 EBACQ-<TBD> |  | AutoCore OS 6.1.X MV88Q515x RFM - EB Zoneo EBACQ-38978 | [5 empty] | Y24-PI1 IP Sprint |  | AutoCore OS 6.1 CORTEXM S32NZ55-R52 DD - EB PMG EBACQ-37751 EBACQ-37810 |  |  |  | AutoCore OS 6.1 CORTEXM S32NZ55-R52 RFM - EB PMG EBACQ-37751 EBACQ-37810 |  |  |  | RTCACM-959 |  |  |  | Y24-PI2 IP Sprint | [7 empty] | Vacation (Plan) | [5 empty] | Y24-PI3 IP Sprint | [9 empty] | Y24-PI4 IP Sprint |  |  | Vacation (Plan) | [10 empty] | Y25-PI1 IP Sprint | [6 empty] | Vacation (Plan) | [6 empty] | Y25-PI2 IP Sprint | [7 empty] | Vacation (Plan) | [5 empty] | Y25-PI3 IP Sprint | [9 empty] | Y25-PI4 IP Sprint |  |  |  | Vacation (Plan) | [9 empty] | Y26-PI1 IP Sprint |  |  |  |  | Vacation (Plan) | [8 empty] | Y26-PI2 IP Sprint | [7 empty] | Vacation (Plan) | [5 empty] | Y26-PI3 IP Sprint | [9 empty] | Y26-PI4 IP Sprint |  |  |  | Vacation (Plan)
Treville | Adil | AutoCore OS 6.1 XPC5777M RFM - Denso EBACQ-35701 EBACQ-39092 Blocker |  |  |  |  | ASCOS-4253 |  | AutoCore OS 6.1.X CYT4BFCCJ - EBACQ-37889 - EBACQ-39601 |  |  |  | AutoCore OS 6.1.X iNDI872XX DD -EBACQ-39087 | [7 empty] | RTCACM-959 |  |  |  | Y24-PI2 IP Sprint | [7 empty] | Vacation (Plan) | [5 empty] | Y24-PI3 IP Sprint | [9 empty] | Y24-PI4 IP Sprint |  |  | Vacation (Plan) | [10 empty] | Y25-PI1 IP Sprint | [6 empty] | Vacation (Plan) | [6 empty] | Y25-PI2 IP Sprint | [7 empty] | Vacation (Plan) | [5 empty] | Y25-PI3 IP Sprint | [9 empty] | Y25-PI4 IP Sprint |  |  |  | Vacation (Plan) | [9 empty] | Y26-PI1 IP Sprint |  |  |  |  | Vacation (Plan) | [8 empty] | Y26-PI2 IP Sprint | [7 empty] | Vacation (Plan) | [5 empty] | Y26-PI3 IP Sprint | [9 empty] | Y26-PI4 IP Sprint |  |  |  | Vacation (Plan)
Treville | Chandru | AutoCore OS 6.1 ARM CV2FS85CR52 DD - Conti AM Lindau EBACQ-37359 EBACQ-<tbd> blocker |  |  |  |  | AutoCore OS 6.1 ARM CV2FS85CR52 RFM - Conti AM Lindau EBACQ-37359 EBACQ-<tbd> blocker | [7 empty] | RTCACM-1091 |  |  |  | RTCACM-957 | [5 empty] | Y24-PI2 IP Sprint | [7 empty] | Vacation (Plan) | [5 empty] | Y24-PI3 IP Sprint | [9 empty] | Y24-PI4 IP Sprint |  |  | Vacation (Plan) | [10 empty] | Y25-PI1 IP Sprint | [6 empty] | Vacation (Plan) | [6 empty] | Y25-PI2 IP Sprint | [7 empty] | Vacation (Plan) | [5 empty] | Y25-PI3 IP Sprint | [9 empty] | Y25-PI4 IP Sprint |  |  |  | Vacation (Plan) | [9 empty] | Y26-PI1 IP Sprint |  |  |  |  | Vacation (Plan) | [8 empty] | Y26-PI2 IP Sprint | [7 empty] | Vacation (Plan) | [5 empty] | Y26-PI3 IP Sprint | [9 empty] | Y26-PI4 IP Sprint |  |  |  | Vacation (Plan)
Treville | Manjunath (28h) | AutoCore OS 6.1 ARM S32NZ55CR52 DD - EB PMG EBACQ-37751 EBACQ-37810 |  |  |  |  | AutoCore OS 6.1.X - SJA1110 - DD - EB PMG EBACQ-39536 EBACQ-39574 | AutoCore OS 6.1.X CORTEXM S32K35X DevDrop - WiTricity EBACQ-39027 EBACQ-39238 |  |  | AutoCore OS 6.1.X CORTEXM S32K35X RFM - WiTricity EBACQ-39027 EBACQ-39238 | [5 empty] | RTCACM-1055 | [7 empty] | Y24-PI2 IP Sprint | [7 empty] | Vacation (Plan) | [5 empty] | Y24-PI3 IP Sprint | [9 empty] | Y24-PI4 IP Sprint |  |  | Vacation (Plan) | [10 empty] | Y25-PI1 IP Sprint | [6 empty] | Vacation (Plan) | [6 empty] | Y25-PI2 IP Sprint | [7 empty] | Vacation (Plan) | [5 empty] | Y25-PI3 IP Sprint | [9 empty] | Y25-PI4 IP Sprint |  |  |  | Vacation (Plan) | [9 empty] | Y26-PI1 IP Sprint |  |  |  |  | Vacation (Plan) | [8 empty] | Y26-PI2 IP Sprint | [7 empty] | Vacation (Plan) | [5 empty] | Y26-PI3 IP Sprint | [9 empty] | Y26-PI4 IP Sprint |  |  |  | Vacation (Plan)
Treville | Pengcheng (Franz) | AutoCore OS 6.1 ARM TDA4VMCR5 RFM - EB PMG EBACQ-36927 | AutoCore OS 6.1 ARM J6FPGADEV1 DD - EB PMG EBACQ-38489 EBACQ-<TBD> |  | AutoCore OS 6.1 ARM TDA4VMCR5 RFM - EB PMG EBACQ-36927 |  | AutoCore OS 6.1.X ARM E36XX RFM (MultiCore)- EBACQ-37731 | Vacation (Plan) | AutoCore OS 6.1.X ARM E36XX RFM (MultiCore)- EBACQ-37731 |  |  |  | AutoCore OS 6.1.X AM6254 TI DD - Internal PMG - EBACQ-39633 |  |  |  | AutoCore OS 6.1.X AM6254 TI RFM - Internal PMG - EBACQ-39633 | [7 empty] | Y24-PI2 IP Sprint | [7 empty] | Vacation (Plan) | [5 empty] | Y24-PI3 IP Sprint | [9 empty] | Y24-PI4 IP Sprint |  |  | Vacation (Plan) | [10 empty] | Y25-PI1 IP Sprint | [6 empty] | Vacation (Plan) | [6 empty] | Y25-PI2 IP Sprint | [7 empty] | Vacation (Plan) | [5 empty] | Y25-PI3 IP Sprint | [9 empty] | Y25-PI4 IP Sprint |  |  |  | Vacation (Plan) | [9 empty] | Y26-PI1 IP Sprint |  |  |  |  | Vacation (Plan) | [8 empty] | Y26-PI2 IP Sprint | [7 empty] | Vacation (Plan) | [5 empty] | Y26-PI3 IP Sprint | [9 empty] | Y26-PI4 IP Sprint |  |  |  | Vacation (Plan)
Treville | Wenjie (Jerry) | ASCOS-7951 |  |  |  | ASCOS-5345 |  | Vacation (Plan) | ASCOS-5345 |  |  |  | AutoCore OS 6.1.X S32K312 RFM - JLR - EBACQ-35074 |  |  |  | AutoCore OS 6.1.X S32K344 RFM - JLR - EBACQ-34904 | [7 empty] | Y24-PI2 IP Sprint | [7 empty] | Vacation (Plan) | [5 empty] | Y24-PI3 IP Sprint | [9 empty] | Y24-PI4 IP Sprint |  |  | Vacation (Plan) | [10 empty] | Y25-PI1 IP Sprint | [6 empty] | Vacation (Plan) | [6 empty] | Y25-PI2 IP Sprint | [7 empty] | Vacation (Plan) | [5 empty] | Y25-PI3 IP Sprint | [9 empty] | Y25-PI4 IP Sprint |  |  |  | Vacation (Plan) | [9 empty] | Y26-PI1 IP Sprint |  |  |  |  | Vacation (Plan) | [8 empty] | Y26-PI2 IP Sprint | [7 empty] | Vacation (Plan) | [5 empty] | Y26-PI3 IP Sprint | [9 empty] | Y26-PI4 IP Sprint |  |  |  | Vacation (Plan)
Treville | Chethan | ASCOS-9287 | [10 empty] | AutoCore OS 6.1.X S32K311 RFM - JLR - EBACQ-36419 |  | Vacation (Plan) | AutoCore OS 6.1.X S32K311 RFM - JLR - EBACQ-36419 |  | Vacation (Plan)
Treville | Jegadeesan | ASCOS-4351 |  |  |  | ASCOS-9242 | [6 empty] | AutoCore OS 6.1.X MWCT2D16S DD - Molex - EBACQ-38753 |  |  |  | AutoCore OS 6.1.X MWCT2D16S RFM - Molex - EBACQ-38753
Treville | Nanditha | [11 empty] | AutoCore OS 6.1.X SAF85XXM7 - Onboarding - RTCACM-1098

## Team_Capacity
Team Velocity Calculation Helper
| Planning data | [6 empty] | Story Points |  |  | Team Members
PI | Sprint | Start | End | Work Days | General % | Unplanned % | Availability % | Capacity | Adjust | Team Velocity | Jeswin Simon Aricatt |  | Kavyashree Eshwar |  | Sathyanarayanan GA(SM) |  | Chandrakant Hugar |  | Jegadeesan K |  | Shivakumar Nadgir |  | Syamkumar NS |  | Chethan R |  | Adil Siddiqui |  | Manjunath Bhavimani |  | Franz |  | Jerry |  | Nanditha |  | Senthil (PO) |  | #15 |  | #16 |  | #17 |  | #18 |  | #19 |  | #20 |  | #21 |  | #22
[11 empty] | Avail. | Absence | Avail. | Absence | Avail. | Absence | Avail. | Absence | Avail. | Absence | Avail. | Absence | Avail. | Absence | Avail. | Absence | Avail. | Absence | Avail. | Absence | Avail. | Absence | Avail. | Absence | Avail. | Absence | Avail. | Absence | Avail. | Absence | Avail. | Absence | Avail. | Absence | Avail. | Absence | Avail. | Absence | Avail. | Absence | Avail. | Absence | Avail. | Absence
Y24-PI2 | S1 | 2024-03-18 | 2024-03-29 | 10 | 10% | 10% | 80% |  |  |  | 100% | 1 | 100% | 1 | 0% | 1 | 100% | 0 | 0% | 1 | 100% | 0 | 100% | 5 | 0% | 0 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 2 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0
| S2 | 2024-04-01 | 2024-04-12 | 10 | 10% | 10% | 80% |  |  |  | 100% | 0 | 100% | 1 | 0% | 1 | 100% | 1 | 0% | 0 | 100% | 9 | 100% | 2 | 0% | 0 | 100% | 0 | 100% | 1 | 100% | 0 | 100% | 0 | 100% | 0 | 0% | 2 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0
| S3 | 2024-04-15 | 2024-04-26 | 10 | 10% | 10% | 80% |  |  |  | 100% | 1 | 100% | 0 | 0% | 1 | 100% | 1 | 100% | 0 | 100% | 1 | 100% | 1 | 100% | 2 | 100% | 1 | 100% | 1 | 100% | 0 | 100% | 0 | 100% | 9 | 0% | 2 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0
| S4 | 2024-04-29 | 2024-05-10 | 10 | 10% | 10% | 80% |  |  |  | 100% |  | 100% |  | 0% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 0%
| S5 | 2024-05-13 | 2024-05-24 | 10 | 10% | 10% | 80% |  |  |  | 100% |  | 100% |  | 0% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 0%
| S6 | 2024-05-27 | 2024-06-07 | 10 | 10% | 10% | 80% |  |  |  | 100% | 0 | 100% | 1 | 0% | 1 | 100% | 1 | 100% | 2 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 9 | 0% | 2 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0
| IP | 2024-06-10 | 2024-06-21 | 10 | 10% | 10% | 80% | - | - | - | 100% | 0 | 100% | 0 | 0% | 0 | 100% | 0 | 100% | 1 | 100% | 0 | 100% | 1 | 100% | 0 | 100% | 0 | 100% | 0 | 100% | 1 | 100% | 1 | 100% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0
India
[9 empty] | PI Velocity: | 278.4
| General Assumptions |  |  |  |  | List of Holidays
| 8 | h/day |  |  |  | 2023-10-02
| 8 | h/story point |  |  |  | 2023-10-24
2023-11-01
2023-11-14

## HW_Planning
PI | Status | ARCH | DERIVATIVE | Test PC | HW: Asset No: (B11005) | HW evaluation Board | MCU: | Person | Start Week | End Week | Start Date | End Date | Comments
Y23-PI4-S1 | FINISHED | CORTEXM | S32K146 | er01329p | #103580 | S32K146EVB-Q144 | FS32K146UAVLQ(-0N73V-QDW2052Y) | Jegadeesan | CW40 | CW43 | 2023-10-02 | 2023-10-27 | Earlier with gcc but to be done with GHS-2021.1.6 Compiler ,This needs to be followed by product Update.To include generator fix
Y23-PI4-S1 | Yes | PA | MPC5777M | B11006 | #924616 + #924600 | MPC57xx Motherboard + MPC5777M_512DS | PPC5777MQMVA8-0N78H-QEMH1413C / cut3 | Adil | CW40 | CW45 | 2023-10-02 | 2023-11-10 | Daughterboard with MPC5777M (BGA512) cut3. Requires MPC57xx Motherboard, e.g. Inv-No.: 924616, SCH-27853 Rev. B, 700-27853 Rev. X1, Leihgabe von Denso
Y23-PI4-S1 | Yes | CORTEXM | S32K34X | B11004 | #101967 | S32K3XXEVB-Q257 | P32K344EHVMMS-0P55A-CTSK2026E | Chethan | CW40 | CW42 | 2023-10-02 | 2023-10-20 | #103490
Y23-PI4-S1 | FINISHED | TRICORE | TC36XD | B11014 | # 103083 | TC3X4L TH V1.0 | SAK-TC364DP-64F300W-AA | Chandru | CW40 | CW45 | 2023-10-02 | 2023-11-10
Y23-PI4-S1 | Yes | ARM | TDA4 | B11005 | #101791 | J721EXSOMG01EVM + J721EXCP01EVM (TDA4) | J721EXCP01EVM (TDA4) | Franz | CW40 | CW45 | 2023-10-02 | 2023-11-10
Y23-PI4-S1 | FINISHED | CORTEXM | iMX8DXL | B10077 | #104124 | MCIMX8DXL-EVK | PIMX8DL-2AVNF-ZAB | Shiva | CW40 | CW41 | 2023-10-02 | 2023-10-13
Y23-PI4-S1 | Yes | ARM | MVQ622X | er01280p | #104018 | EV-DB-MV-Q6223-A0-1 | MV-Q6223-WT-170AA-P69T520.2-2310-A0E-TW-ES | Jeswin | CW40 | CW42 | 2023-10-02 | 2023-10-20
Y23-PI4-S1 | FINISHED | RH850 | RH850F1K | B11001 | #925225 (PB) + #102787 (MB) | Y-RH850-F1X-100PIN-PB-T1-V2 + RH850-X1X-MB-T1-V1 | R7F7016214(-3TC-2237-TJ21214) | Syam | CW40 | CW41 | 2023-10-02 | 2023-10-13
Y23-PI4-S1 | FINISHED | TRICORE | TC38XQ | B12043 | #102703 | TC3X7 TH V2.01 | SAK-TC387QP-160F300S-AA-EES | Jery | CW40 | CW41 | 2023-10-02 | 2023-10-13
Y23-PI4-S1 | Yes | CORTEXM | S32Z27XLLCE | B11009 | 103178 | S32Z27X-DC Daughter Board | P32Z270ADCK0MJFT(-P65C-ATTJ2207A)-E5x | Kavya | CW40 | CW42 | 2023-10-02 | 2023-10-20
Y23-PI4-S1 | FINISHED | TRICORE | TC4DXX | B11007 | #104062 | TC4X9 COM V1.0 | SAA-TC4D9XE-20MF500CC-AA-EES (3FT6R616H01-GE324) | Manjunath | CW40 | CW42 | 2023-10-02 | 2023-10-20
Y23-PI4-S1 | FINISHED | CORTEXM | S32K14X | er01267p | #101616 | S32K144EVB-Q100 | PS32K144-HAMLL-0N57U-QWA1930E | Sathya | CW40 | CW43 | 2023-10-02 | 2023-10-27 | #101825 - JLR - S32K2x - 2 dual Core - S32K24
Y23-PI4-S1 |  |  |  | B10076 | [6 empty] | 2023-10-02 | 2023-10-27
Y23-PI4-S2 | Yes | ARM | CV2FS85CR52 | B10077 | 104095 | CV2FS Dev. Kit main board | AB023-202-V11 | Chandru | CW42 | CW50 | 2023-10-16 | 2023-12-15
Y23-PI4-S2 | FINISHED | TRICORE | TC33XL | B11014 | #103691 | TC333 TH V1.0 | SAK-TC333LP-32F300F-AA-ES | Jery | CW42 | CW43 | 2023-10-16 | 2023-10-27 | Conti requali-
Y23-PI4-S3 | Yes | CORTEXM | S32K311 | B11001 | #104301 | Molex Manta Ruby 2 (MAGR) M16 | MWCT2016SHVPA(-0P09C-CTAA2318B) | Syam | CW46 | CW47 | 2023-11-13 | 2023-11-24 | Molex MWCT-2016S - Customer Board
Y23-PI4-S3 | FINISHED | CORTEXM | CYT4BB | B12043 | 104277 | CYTVII-B-H-176-SO | CYT4BB8CEBES(-148VV003-B-10-CYP-TWN-C) | Shiva | CW45 | CW47 | 2023-11-06 | 2023-11-24 | CYT4BB HW waiting- Will Rxd by 26-Oct
Y23-PI4-S3 | FINISHED | CORTEXM | CYT2B9X | B11014 | #103784 | CYTVII-B-E-1M-SK | CYT2B95CACQ0AZ(-10344063-C-10-SGS-CYP-JPN-C) | Jery | CW44 | #NAME? | 2023-10-30 | 2023-11-10 | Conti requali-
Y23-PI4-S3 | NA | ARM | S32NZ55CR52 | B11007 | #104339 | ? | WAITING TO RECEIVE | Manjunath | CW46 | CW52 | 2023-11-13 | 2023-12-29
Y23-PI4-S3 | FINISHED | CORTEXM | SAF8544 | er01267p | #104229 | X-STRX-ANT-KIT-A | SAF8544-B1(-T6R740.L1-01-Y0rD23231X-13-X12-X13) | Sathya | CW44 | CW45 | 2023-10-30 | 2023-11-10
Y23-PI4-S3 | FINISHED | CORTEXM | S32K146 | er01329p | #104279 | S32K146EVB-Q144 | PS32K146UAVLQ-0N73V-QAC1735E | Jegadeesan | CW44 | CW46 | 2023-10-31 | 2023-11-17 | Swapped the JLR board with Autoliv Board as JLR board need by ACP team ( Rutuja)
Y23-PI4-S3 | FINISHED | PA | MPC5777M | B11006 | #104283 , #104286 | MPC57xx Motherboard + MPC5777M_512DS | PPC5777M2MVA8B-0N50N-QAA1448B | Adil | CW45 | CW48 | 2023-11-06 | 2023-11-27 | Daughterboard with MPC5777M (BGA512) cut3. Requires MPC57xx Motherboard, e.g. Inv-No.: 924616, SCH-27853 Rev. B, 700-27853 Rev. X1, Leihgabe von Denso
Y23-PI4-S4 | FINISHED | CORTEXM | CYT2B7X | B11014 | #103590 | CYTVII-B-E-176-CPU | CYT2B75CADES(-03444512-D-10-CYP-JPN-C) | Jery | CW46 | CW47 | 2023-11-13 | 2023-11-24 | Conti requali-
Y23-PI4-S3 | OPEN | CORTEXM | SAF8544 | er01267p | #104229 | X-STRX-ANT-KIT-A | SAF8544-B1(-T6R740.L1-01-Y0rD23231X-13-X12-X13) | Chethan | CW46 | CW47 | 2023-11-13 | 2023-11-24
Y24-PI1-S2 | No | ARM | MVQ515X | B11004 | #104355 | 88Q5152 REV B | 88Q5152-DGH2-P69F280.5ES-2251-B1PN2-TW-ES | Sathya | CW50 | CW3 | 2023-12-11 | 2024-01-19
Y24-PI1-S2 | No | ARM | E36XX | B11014 | 103971 | SD109_E3600_BGA 324_DEV_KIT Rev. A01 | E3640-AGKAACS(-020501002238C1) | Jerry | CW51 | CW9 | 2023-12-19 | 2024-03-01
Y24-PI1-S2 | No | RH850 | RH850U2BX | er01267p | 103931 + 103933 | Y-RH850-U2B-468PIN-PB-T1-V1 + Y-RH850-XIX-MB-T1-V1 Evaluation Platform | ? | Chethan | CW51 | CW9 | 2023-12-19 | 2024-03-01
Y24-PI1-S3 | No | CORTEXM | S32K14X | B12043 | #104405/6/7 | S32K146EVB-Q144 | PS32K146UAVLQ-0N73V-QDW2052T | Shiva | CW2 | CW5 | 2024-01-08 | 2024-02-02
Y24-PI1-S3 | No | CORTEXM | S32K35X | er01329p | #104416/7/8/9 | TJA1145A-EVB | ??? | Syam | CW2 | CW9 | 2024-01-08 | 2024-03-01
Y24-PI1-S6 | No | CORTEXM | S32K34X | B11006 | #104081 | S32K3X4EVB-T172 | P32K344EHVPBS 0P55A CTZQ2213A | Shiva | CW08 | CW11 | 2024-01-19 | 2024-03-08
Y24-PI1-S6 | FINISHED | CORTEXM | CYT4BF | B11005 | #104533/ #104534 | CTVYII-B-H-8M-320-CPU Traveo II Evaluation Board | CYT4BFCCHDES-02988902-D-10 | Adil | CW8 | CW12 | 2024-02-21 | 2024-03-22
Y24-PI1-S6 | No | CORTEXM | SJA1110X | B11001 | #104551 | SJA1110-EVM | SJA1110A-TR7X5434.000-04-sS23030 | Syam | CW8 | CW18 | 2024-02-21 | 2024-05-03
Y24-PI1-IP | Yes | CORTEXM | CYT3DL | B11004 | #102066 | CYTVII-C-2D-4M-216-CPU | CYT3DL-ABHAES | Jegadeesan | CW10 | CW11 | 2024-03-07 | 2024-03-15
Y24-PI1_IP | Yes | RH850 | RH850P1HC | B11007 | #100714 | RH850-X1X-MB-T2-V1 + RH850-P1XC-292PIN-PB-T1-V2 | R7F701371EABG-C | Jerry | CW10 | CW11 | 2024-03-07 | 2024-03-15
Y24-PI1-IP/Y24-PI2 | No | ARM | AM62XX | B11005 | #104655/#104656 | SK-AM62 | Not Available | Franz | CW11 | CW20 | 2024-03-12 | 2024-05-17
Y24-PI2 | No | CORTEXM | iNDI872XX | B11007 | #104566 /#104567. | UQI FB FFB4 PCBA Eval Board | iND87200 ES 79353.09 2229 | Adil | CW11 | CW20 | 2024-03-15 | 2024-05-17
Y24-PI2 | No | CORTEXM | MWCT2D1XS | B11009 | #104571 | NXP WCT15WAUTOS2MD Rev. B | PWCT2D16SHVPA 0P97C CZSL2322A | Jegadeesan | CW11 | CW20 | 2024-03-15 | 2024-05-17
Y24-PI2 | No | ARM | MV88Q515X | B12043 | #104355 | 88Q5152 REV B | 88Q5152-DGH2-P69F280.5ES-2251-B1PN2-TW-ES | Jeswin | CW11 | CW13 | 2024-03-15 | 2024-03-29
Formulas:
Start Week = CONCATENATE("CW",WEEKNUM([Start Date],1))
End Week = CONCATENATE("CW",WEEKNUM([End Date],1))